## Document Control
Classification | Restricted
Contents
TAB | DESCRIPTION
OPEN | Contains records of internal and external audit findings
CLOSED | Contains records of internal and external audit findings

## OPEN
Item# | System | Type | Source | Source Ref | Division/Group | Owner | Description | Root Cause | Root Cause Description | Priority | Initial Date | Initial Deadline | New Deadline | Close Date | Effectiveness | Comment
8 | ISMS | OFI | Internal | Internal Audit # | Group - Risk & Compliance | M. Woolard | Description of what to improve 1 | Incomplete process | 5 why's root cause | Standard | 2019-01-01 | 2019-01-31 | 2019-02-28 |  |  | Review May 2018 - Group documents into sensible sets, Quality & Governance to create list and publish. Guidelines on retention including schedule, storage, handling & disposal of records and information. Inventory of sources for key information. 03/10/18 - Doc A8.2 cover protection of "Classified" information. Record retention policy is outstanding. 31/10/18 - In progress JSM to drop Ron P. a note on record retention for Quality Records 07/11/18 - Review with R&C 12/12/18 - MW to look at for R&C 06/02/19 - No progress. 06/03/19 - In progress.
9 | ISMS | OFI | External | External Audit # | Systems Engineering | M. Woolard | Description of what to improve 2 | Ineffective Education | 5 why's root cause | High | 2019-01-01 | 2019-04-30 | 2019-06-30 |  |  | 03/10/18 - Reassigned to CTO 12/12/18 - R&C to complete a list of approved encryption methods/tools. 06/02/19 No progress 06/03/19 - In progress target June

## CLOSED
Item# | System | Type | Source | Source Ref | Division/Group | Owner | Description | Root Cause | Root Cause Descritpion | Priority | Initial Date | Initial Deadline | New Deadline | Close Date | Effectiveness | Comment | #VALUE!